## NCT 8-Stack Project
Contact Info | Task Name | Completed | Keys | Duration | Start | Finish | Predecessors | Assigned To | Status | Work Performed | Comments
Owner Info | Phase 1 - Demo | - | - | 2 | 2013-09-16 | 2013-09-17 |  | BMC
Arslanian, Norair | Unit #98 | TRUE | TRUE | 2 | 2013-09-16 | 2013-09-17 |  | Tito & Russ | Complete
Smith, Richard | Unit #88 | TRUE | TRUE | 2 | 2013-09-16 | 2013-09-17 |  | Tito & Russ | Complete
Chalhoub, Michel | Unit #78 | TRUE | TRUE | 2 | 2013-09-16 | 2013-09-17 |  | Tito & Russ | Complete
Petrosian, Sebuh | Unit #68 | TRUE | TRUE | 2 | 2013-09-16 | 2013-09-17 |  | Tito & Russ | Complete
Kocharians, Torgom | Unit #58 | TRUE | TRUE | 2 | 2013-09-16 | 2013-09-17 |  | Tito & Russ | Complete
Markarian, Nelik | Unit #48 | TRUE | TRUE | 2 | 2013-09-16 | 2013-09-17 |  | Tito & Russ | Complete
Kocharians, Torgom | Unit #38 | TRUE | TRUE | 2 | 2013-09-16 | 2013-09-17 |  | Tito & Russ | Complete
Schultz, Peter | Unit #28 | TRUE | TRUE | 2 | 2013-09-16 | 2013-09-17 |  | Tito & Russ | Complete
Tenant Info | Phase 2 - Plumbing Work | - | - | 5 | 2013-09-18 | 2013-09-24 | 1 | Houghton Plumbing
| Unit #98 | TRUE | - | 5 | 2013-09-18 | 2013-09-24 |  | Houghton Plumbing | Complete
| Unit #88 | TRUE | - | 5 | 2013-09-18 | 2013-09-24 |  | Houghton Plumbing | Complete
| Unit #78 | TRUE | - | 5 | 2013-09-18 | 2013-09-24 |  | Houghton Plumbing | Complete
| Unit #68 | TRUE | - | 5 | 2013-09-18 | 2013-09-24 |  | Houghton Plumbing | Complete
| Unit #58 | TRUE | - | 5 | 2013-09-18 | 2013-09-24 |  | Houghton Plumbing | Complete
| Unit #48 | TRUE | - | 5 | 2013-09-18 | 2013-09-24 |  | Houghton Plumbing | Complete
| Unit #38 | TRUE | - | 5 | 2013-09-18 | 2013-09-24 |  | Houghton Plumbing | Complete
| Unit #28 | TRUE | - | 5 | 2013-09-18 | 2013-09-24 |  | Houghton Plumbing | Complete
| Phase 3 - Closing | - | - | 27 | 2013-09-26 | 2013-11-01 |  | BMC
| Unit #98 | TRUE |  | 5 | 2013-09-26 | 2013-10-02 |  | Tito & Max | Complete
| Unit #88 | TRUE |  | 4 | 2013-09-26 | 2013-10-01 |  | Tito & Max | Complete
| Unit #78 | TRUE |  | 4 | 2013-09-26 | 2013-10-01 |  | Tito & Max | Complete
| Unit #68 | TRUE |  | 6 | 2013-10-03 | 2013-10-10 |  | Tito & Kenny | Complete
| Unit #58 | TRUE |  | 8 | 2013-10-03 | 2013-10-14 |  | Tito, Max & Kenny | Complete |  | Per request & approval by board: paint affected areas
| Unit #48 | TRUE |  | 6 | 2013-10-08 | 2013-10-15 |  | Tito & Max | Complete
| Unit #38 | TRUE |  | 1 | 2013-11-01 | 2013-11-01 |  | Tito & Max | Complete |  | Away on vacation - unable to close
| Unit #28 | TRUE |  | 5 | 2013-10-10 | 2013-10-16 |  | Tito & Max | Complete
|  |  |  | Total Hours |  | Date | Week 1 | Tito | Max | Russ | Kenny
|  |  |  | 26 |  | 2013-09-26 |  | 8 | 8 | 0 | 0
[6 empty] | 2013-09-27 |  | 5 | 5 | 0 | 0
[6 empty] | Date | Week 2 | Tito | Max | Russ | Kenny
|  |  |  | 66 |  | 2013-09-30 |  | 5 | 5 | 0 | 0
[6 empty] | 2013-10-01 |  | 8 | 8 | 0 | 0
[6 empty] | 2013-10-02 |  | 6 | 6 | 0 | 0
[6 empty] | 2013-10-03 |  | 6 | 6 | 0 | 0
[6 empty] | 2013-10-04 |  | 8 | 8 | 0 | 0
|  |  |  | 80 |  | Date | Week 3 | Tito | Max | Russ | Kenny
[6 empty] | 2013-10-07 |  | 8 | 8 | 0 | 0
[6 empty] | 2013-10-08 |  | 8 | 0 | 4 | 0
[6 empty] | 2013-10-09 |  | 8 | 7 | 0 | 8
[6 empty] | 2013-10-10 |  | 8 | 0 | 4 | 0
[6 empty] | 2013-10-11 |  | 8 | 8 | 1 | 0
[6 empty] | Date | Week 4 | Tito | Max | Russ | Kenny
|  |  |  | 30 |  | 2013-10-14 | Holiday | 0 | 0 | 0 | 0
[6 empty] | 2013-10-15 |  | 8 | 8 | 0 | 0
[6 empty] | 2013-10-16 |  | 7 | 7 | 0 | 0
|  |  | Hours: | 202
|  |  | Cost @45/hr | 9090
|  |  | Labor+ Materials: | 10552.46 |  | Purchase Date | Vendor |  | Total |  | Materials
[6 empty] | 2013-09-26 | Arlington Coal | & Lumber | 47.26 |  | 4x8' sheetrock (qty. 4)
[6 empty] | 2013-09-26 | Arlington Coal | & Lumber | 89.68 |  | 48" therma-fiber fire rated insulation & batts
[6 empty] | 2013-09-30 | Arlington Coal | & Lumber | 47.26 |  | 4x8' sheetrock (qty. 4)
[6 empty] | 2013-10-01 | Arlington Coal | & Lumber | 3.29 |  | 2x4x96" spruce
[6 empty] | 2013-10-02 | Arlington Coal | & Lumber | 47.26 |  | 4x8' sheetrock (qty. 4)
[6 empty] | 2013-10-03 | Arlington Coal | & Lumber | 64.05 |  | 4x8 sheetrock (qty. 4), USG #800 mesh mini-bead 8' (qty. 4)
[6 empty] | 2013-10-09 | Arlington Coal | & Lumber | 79.25 |  | contractor trash bags, drywall screws, drywall mud pan, flex drywall scraper, flex drywall joint knife, 8" drywall joint knife, 4x8' sheetrock (qty. 2)
[6 empty] | 2013-09-26 | City Paint | & Supply | 22.28 |  | 1 gal joint compound, retractable utility knife & 6-in-1 painters tool
[6 empty] | 2013-10-01 | City Paint | & Supply | 12.73 |  | 2 retractable utility knives
[6 empty] | 2013-10-03 | City Paint | & Supply | 54.57 |  | 6" flex joint knife, 10" stainless taping knife, 1 gal joint compound, 9x12 drop cloth
[6 empty] | 2013-10-04 | City Paint | & Supply | 22.81 |  | 1 gal joint compound, coarse drywall screws, self adhesive tape
[6 empty] | 2013-10-07 | City Paint | & Supply | 14.33 |  | 1 gal joint compound, self adhesive tape
[6 empty] | 2013-10-08 | City Paint | & Supply | 26.01 |  | 5 gal joint compound & super glue
[6 empty] | 2013-10-09 | City Paint | & Supply | 25.48 |  | 10qt mixing pail, 10lb drylok fast plug
[6 empty] | 2013-10-10 | City Paint | & Supply | 20.48 |  | angle sand sponges (qty. 2), extra large sponge
[6 empty] | 2013-10-11 | City Paint | & Supply | 121.22 |  | 2.5" angle latex brush, liner for deep metal tray, box of respirators, 5 heavy duty blades, prefilter, paint respirator, painters caulk, 1 lb rags, 9x400 clear poly film
[6 empty] | 2013-10-11 | City Paint | & Supply | 31.85 |  | 1.5" chip brush, Regal Aquaglo pastel base paint, 1 gal joint compound
[6 empty] | 2013-10-15 | City Paint | & Supply | 7.29 |  | microfiber roller covers and switch plates
[6 empty] | 2013-10-15 | City Paint | & Supply | 44.58 |  | 1 gal Aquaglo white paint
[6 empty] | 2013-10-28 | City Paint | & Supply | 11.68 |  | 20 ct. contractor bags
[6 empty] | 2013-09-27 | Home Depot |  | 293.19 |  | 18x18 metal access panels (qty. 7) & 50' ext. cords (qty. 2)
[6 empty] | 2013-10-07 | Home Depot |  | 115.83 |  | 8x8 metal access door & 18x18 metal access door (4 total)
[6 empty] | 2013-10-10 | Home Depot |  | 54.4 |  | 2x2 ceiling tiles
[6 empty] | 2013-09-26 | Shattucks |  | 49.88 |  | T-square, 30' tape rule, carpenter pencil, safety glasses, drywall screws
[6 empty] | 2013-09-30 | Shattucks |  | 17.54 |  | 5 qt. multi-mix container, texture roller, roller frame, paint liner
[6 empty] | 2013-10-10 | Shattucks |  | 46.93 |  | 5 gal plastic pale, roller frames (qty. 2), 9x12 drop cloths (qty. 2), 1 lb roll texture (qty. 2), roller texture (qty. 2), paint trays (qty. 2)
[6 empty] | 2013-10-15 | Shattucks |  | 71.06 |  | roller (qty. 2), chip brush, blank wallplates (qty.2), plastic paint tray, 8pk apron, 1 gal flat white ceiling paint
[6 empty] | 2013-10-15 | Shattucks |  | 20.27 |  | 36oz bona wood floor cleaner, swiffer sweeper
[5 empty] | Total Materials: |  |  |  | 1462.46