## NCT 2-Stack Project
Contact Info | Task Name | Completed | Keys | Duration | Start | Finish | Predecessors | Assigned To | Status | Work Performed | Comments
Owner Info | Phase 1 - Demo | - | - | 8 | 2013-10-21 | 2013-10-30
Arslanian, Norair | Unit #92 | TRUE |  | 1 | 2013-10-28 | 2013-10-28 |  | Kenny & Max | Complete | opened 3' walls in bdrm floor to ceiling | No keys, would like to be home
Smith, Richard | Unit #82 | TRUE | TRUE | 1 | 2013-10-28 | 2013-10-28 |  | Kenny & Max | Complete | opened the wall, took out sheet rock | CAT in unit please be careful! If not home, keys will be with unit #84
Chalhoub, Michel | Unit #72 | TRUE |  | 1 | 2013-10-28 | 2013-10-28 |  | Kenny & Max | Complete | opened the wall, took out sheet rock
Petrosian, Sebuh | Unit #62 | TRUE | TRUE | 1 | 2013-10-22 | 2013-10-22 |  | Tito & Max | Complete | open walls in bdrm
Kocharians, Torgom | Unit #52 | TRUE | TRUE | 1 | 2013-10-21 | 2013-10-21 |  | Tito & Max | Complete | Need to fully open. Pull kitchen ceiling tiles down. Open back bdrm soffit. Hold off on soffit in back hallway.
Markarian, Nelik | Unit #51 | TRUE | [5 empty] | Houghton | Complete | open sofft (bottom & front) & kt risers | open section of wall adj. to #52 to connect new piping to old piping
Kocharians, Torgom | Unit #42 | TRUE | TRUE | 1 | 2013-10-21 | 2013-10-21 |  | Tito & Max | Complete | open walls in bdrm
Schultz, Peter | Unit #32 | TRUE |  | 1 | 2013-10-30 | 2013-10-30 |  | TIto & Max | Complete | open 3' walls in bdrm floor to ceiling
Kaze, Micher | Unit #22 | TRUE |  | 1 | 2013-10-30 | 2013-10-30 |  | Tito & Max | Complete | open 3' walls in bdrm floor to ceiling
Tenant Info | Phase 2 - Plumbing Work | - | - | 3 | 2013-10-31 | 2013-11-04
| Unit #92 | TRUE | - | 3 | 2013-10-31 | 2013-11-04 |  | Houghton | Complete
| Unit #82 | TRUE | - | 1 | 2013-10-31 | 2013-10-31 |  | Houghton | Complete
| Unit #72 | TRUE | - | 1 | 2013-10-31 | 2013-10-31 |  | Houghton | Complete
| Unit #62 | TRUE | - | 1 | 2013-10-31 | 2013-10-31 |  | Houghton | Complete
| Unit #52 | TRUE | - | 3 | 2013-10-31 | 2013-11-04 |  | Houghton | Complete
| Unit #51 | TRUE | - | 1 | 2013-10-31 | 2013-10-31 |  | Houghton | Complete
| Unit #42 | TRUE | - | 2 | 2013-11-01 | 2013-11-04 |  | Houghton | Complete
| Unit #32 | TRUE | - | 2 | 2013-11-01 | 2013-11-04 |  | Houghton | Complete
| Unit #22 | TRUE | - | 2 | 2013-11-01 | 2013-11-04 |  | Houghton | Complete
| Phase 3 - Closing | - | - | 14 | 2013-10-28 | 2013-11-14
| Unit #92 | TRUE | - | 6 | 2013-11-07 | 2013-11-14 |  | Tito & Kenny | Complete |  | Request to be home for access
| Unit #82 | TRUE | - | 3 | 2013-11-05 | 2013-11-07 |  | Tito & Kenny | Complete
| Unit #72 | TRUE | - | 4 | 2013-11-04 | 2013-11-07 | 15FS +1 day | Tito & Kenny | Complete |  | Requested to be painted (per owner approval)
| Unit #62 | TRUE | - | 4 | 2013-11-04 | 2013-11-07 | 16FS +1 day | Tito & Kenny | Complete
| Unit #52 | TRUE | - | 4 | 2013-10-28 | 2013-10-31 |  | Tito & Max | Complete | Partial close as Houghton is not complete yet, then fully close | Unit owner painted before BMC finished - only one coat on & no sanding
| Unit #51 | TRUE | - | 4 | 2013-10-28 | 2013-10-31 |  | Tito & Max | Complete
| Unit #42 | TRUE | - | 4 | 2013-10-28 | 2013-10-31 |  | Tito & Kenny | Complete
| Unit #32 | TRUE | - | 3 | 2013-11-06 | 2013-11-08 |  | Tito & Max | Complete
| Unit #22 | TRUE | - | 3 | 2013-11-06 | 2013-11-08 |  | Tito & Max | Complete
|  |  | Total Hours |  |  | Date | Week 1 | Tito | Max | Russ | Kenny
|  |  | 16 |  |  | 2013-10-21 |  | 4 | 4 | 0 | 0
[6 empty] | 2013-10-22 |  | 4 | 4 | 0 | 0
[6 empty] | 2013-10-23 |  | 0 | 0 | 0 | 0
[6 empty] | 2013-10-24 |  | 0 | 0 | 0 | 0
[6 empty] | 2013-10-25 |  | 0 | 0 | 0 | 0
|  |  | 52 |  |  | Date | Week 2 | Tito | Max | Russ | Kenny
[6 empty] | 2013-10-28 |  | 0 | 3 | 0 | 3
[6 empty] | 2013-10-29 |  | 8 | 8 | 0 | 0
[6 empty] | 2013-10-30 |  | 7 | 7 | 0 | 0
[6 empty] | 2013-10-31 |  | 8 | 3 | 0 | 0
[6 empty] | 2013-11-01 |  | 5 | 0 | 0 | 0
|  |  | 46 |  |  | Date | Week 3 | Tito | Max | Russ | Kenny
[6 empty] | 2013-11-04 |  | 7 | 0 | 0 | 4
[6 empty] | 2013-11-05 |  | 0 | 0 | 0 | 0
[6 empty] | 2013-11-06 |  | 8 | 0 | 8 | 0
[6 empty] | 2013-11-07 |  | 7 | 7 | 0 | 0
[6 empty] | 2013-11-08 |  | 5 | 0 | 0 | 0
|  |  | 25 |  |  | Date | Week 4 | Tito | Max | Russ | Kenny
[6 empty] | 2013-11-11 | Veteran's Day | 0 | 0 | 0 | 0
[6 empty] | 2013-11-12 |  | 6 | 6 | 0 | 0
[6 empty] | 2013-11-13 |  | 5 | 5 | 0 | 0
|  | Hours: | 139 |  |  | 2013-11-14 |  | 3 | 0 | 0 | 0
|  | Cost @45/hr | 6255 |  |  | 2013-11-15 |  | 0 | 0 | 0 | 0
|  | Labor+ Materials: | 6740.11
[6 empty] | Purchase Date | Vendor |  | Total |  | Materials
[6 empty] | 2013-10-29 | Arlington Coal | & Lumber | 58.23 |  | 1/2" 4x8 sheetrock (qty. 2), 8' drywall dura bead (qty. 4)
[6 empty] | 2013-10-29 | Arlington Coal | & Lumber | 23.63 |  | 1/2" 4x8 sheetrock (qty. 2)
[6 empty] | 2013-10-30 | Arlington Coal | & Lumber | 59.7 |  | 3x16 48" therma-fiber fire rated insulation (53.3 sq ft)
[6 empty] | 2013-11-04 | Arlington Coal | & Lumber | 23.63 |  | 1/2" 4x8 sheetrock (qty. 2)
[6 empty] | 2013-11-06 | Arlington Coal | & Lumber | 43.39 |  | 1/2" 4x8 sheetrock (qty. 2), 2x4x96" Spruce (qty. 6)
[6 empty] | 2013-11-07 | Arlington Coal | & Lumber | 11.82 |  | 1/2" 4x8 sheetrock (qty. 1)
[6 empty] | 2013-10-28 | City Paint | & Supply | 31.86 |  | 2"x55yd duct tape, 10'x100' 2mil clear poly film
[6 empty] | 2013-10-28 | City Paint | & Supply | 8.27 |  | heavy duty blades (qty. 5), retractable utility knife
[6 empty] | 2013-10-28 | City Paint | & Supply | 11.68 |  | contractor garbage bags
[6 empty] | 2013-10-29 | City Paint | & Supply | 27.7 |  | contractor garbage bags, torpedo level & comb square
[6 empty] | 2013-11-14 | City Paint | & Supply | 54.15 |  | sandpaper, 4 3/16"x11" d/w screen 10pk, 4 3/16"x11" 220D d/w screen 10pk & gal light joint compound
[6 empty] | 2013-11-12 | Home Depot |  | 11.54 |  | solid doorstop, 4x48x80 wall base
[6 empty] | 2013-10-29 | Shattucks |  | 27.37 |  | 6-in-1 painters tool, joint cement, drywall screws
[6 empty] | 2013-11-06 | Shattucks |  | 33.11 |  | drywall screws, joint cement (qty. 2), cement trowel
[6 empty] | 2013-11-07 | Shattucks |  | 17.19 |  | joint cement (qty. 2)
[6 empty] | 2013-11-13 | Shattucks |  | 23.84 |  | rigid door stop, switch box supports, saw keyhole hand nest
[5 empty] | Total Materials: |  |  |  | 485.11

## Discussions
Row 3 | Discussion Title | Keys | Bill Anastasia | 10/25/13 1:09 PM
| Comments | Tenant will leave keys with Unit 84 if she steps out next week. Unit 84 owner is homebound. | Bill Anastasia | 10/25/13 1:09 PM
Row 5 | Discussion Title | Keys | Mary Lapasaran | 10/21/13 12:23 PM
| Comments | Tito dropped key off to Kevin at the property | Mary Lapasaran | 10/22/13 10:43 AM
|  | We only have the key to the top lock - they will leave the bottom unlocked | Mary Lapasaran | 10/22/13 5:53 AM
|  | Alarm on door - need code | Mary Lapasaran | 10/21/13 1:02 PM
|  | Bill will get keys this afternoon from tenants - can access and do demo tomorrow (10-22-13) | Mary Lapasaran | 10/21/13 12:23 PM
Row 6 | Discussion Title | Received keys 10-17-13 | Mary Lapasaran | 10/17/13 7:54 AM
| Comments | Bill will give keys to Kevin - Houghton | Mary Lapasaran | 10/22/13 5:54 AM
|  | Received keys from Torgom 10-17-13 | Mary Lapasaran | 10/17/13 7:54 AM
Row 8 | Discussion Title | Received keys | Mary Lapasaran | 10/17/13 7:55 AM
| Comments | Kenny gave keys to Kevin from Houghton plumbing and he has our BMC#1 shopvac | Mary Lapasaran | 10/28/13 9:10 AM
|  | Bill will give keys to Kevin - Houghton | Mary Lapasaran | 10/22/13 5:54 AM
|  | Received keys from Torgom 10-17-13 | Mary Lapasaran | 10/17/13 7:55 AM
Row 28 | Discussion Title | Unit #52 Closing | Mary Lapasaran | 10/16/13 12:47 PM
| Comments | 52 will be done Monday - it is all closed up, but we need to go back tmrw and Friday to apply a few more coats of compound. | Mary Lapasaran | 10/30/13 12:16 PM
|  | Kevin from Houghton can show guys what can be closed up ASAP. Soffit can be started and half of the bedroom wall. Please let me know when this has started. | Bill Anastasia | 10/28/13 8:51 AM
|  | Torgom agreed on 10/16/13 during the walk thru that during the closing of the soffit we could just close it flat w/ NO popcorn! | Mary Lapasaran | 10/16/13 12:47 PM
Row 29 | Discussion Title | Unit #51 | Mary Lapasaran | 11/04/13 5:41 AM
| Comments | Tito will go back today for a few minutes, just needs a "touch-up" | Mary Lapasaran | 11/04/13 5:41 AM